## SUMMERY OF WORK
M/S FUTURE PROJECTS
WORK ORDER SUMMARY RECEIVED DIRECTLY FROM CGD COMPANY
CORPORATE OFF-03 & 04, GROUND FLOOR, SOLITAIRE II, BLDG. NO-10, OPP- SAMRUDDHI BLDG., POONAM GARDEN, MIRA ROAD(E), THANE-401107
SN. | WORK ORDER RECD. FROM | NATURE OF JOB | WORK ORDER /PURCHASE ORDER NO | AREA | WORK ORDER DETAILS
[5 empty] | WORK ORDER DATE | LAST DATE OF WORK ORDER | WORK ORDER VALUE | WORK BILLING EXECUTED VALUE | PERIOD IN MONTH | % | REMARKS
1 | M/S MAHANAGAR GAS LTD., | ARC FOR RELAYING & RECTIFICATION | MGL/C&P//4100002318/2012-13/BB | MGL/C&P//4100002318/2012-13/BB | 15.01.2012 | 15.01.2013 | 1425680 | 1405488.64 | 12 | 98.5837 | COMPLETED
2 | M/S MAHANAGAR GAS LTD., | ARC FOR RELAYING & RECTIFICATION | MGL/C&P//4100002666/2012-13/BB | MGL/C&P//4100002666/2012-13/BB | 30.05.2012 | 14.01.2013 | 712840 | 712317.5 | 8 | 99.9267 | COMPLETED
3 | M/S MAHANAGAR GAS LTD., | Laying of ERW-GI/Copper Pipe, Installation of Gas Meter, Rubber Hose, Vlaves etc. for supply of pipe natural gas inside the Kitchen for Domestic Customers in PANVEL Area SPREAD XI DRS127 | MGL/C&P//4100002824/2012/PM | MGL/C&P//4100002824/2012/PM | 01.10.2012 | 31.12.2013 | 15819725 | 3602153.38 | 15 | 22.77 | COMPLETED
4 | M/S MAHANAGAR GAS LTD., | ARC FOR RELAYING & RECTIFICATION | MGL/C&P//4100002928/2012-13/BB | MGL/C&P//4100002928/2012-13/BB | 10.12.2012 | 31.01.2014 | 1332279 | 1304001 | 12 | 97.8775 | COMPLETED
5 | M/S MAHANAGAR GAS LTD., | AMC for Domestic Customer | MGL/C&P/4100003197/2013-14/BB dtd. 05.04.2013 | MGL/C&P/4100003197/2013-14/BB dtd. 05.04.2013 | 01.04.2013 | 31.03.2014 | 5313900 | 4861168.5 | 12 | 91.4802 | COMPLETED
6 | M/S MAHANAGAR GAS LTD., | Annual Rate contrat for Permanent Disconnection of Domestic Customers who have defaulted in Payment | MGL/C&P/O&M/0323/2012-13/BB | MGL/C&P/4100003215/2012-13/BB | 20.04.2013 | 19.04.2014 | 4425000 | 1523750 | 12 | 34.435 | COMPLETED
7 | M/S MAHANAGAR GAS LTD., | Erection of GI Pipe, Copper Tube, Installation of Gas Meter, Rubber Hose, Valves etc. for supply of Piped Natural Gas inside the kitchen | MGL/C&P/PLNG/0469/13-14/PM Dated: 25.06.2013 | MGL/C&P//4100003527/13/PM Dated: 25.09.2013 | 01.10.2013 | 30.09.2015 | 40050607 | 35449590 | 24 | 88.512 | COMPLETED
8 | M/S MAHANAGAR GAS LTD., | Providing PNG connections from existing gasified risers (Online Tap-off.) of GI Pipe Network Zone D Thane & Mira Road Area | MGL/C&P/PLNG/0529/13-14/PM Dated: 02.08.2013 | MGL/C&P//4100003544/13/PM Dated: 05.10.2013 | 01.10.2013 | 30.09.2015 | 20637439 | 17998787 | 24 | 87.2142 | COMPLETED
9 | M/S MAHANAGAR GAS LTD., | Laying of MP,LP pipe line in DRS 135A, Ambernath *E Area KDAB Zone | MGL/C&P/CA2 PRJECTS/0926/14-15/PM Dated: 05.08.2014 | MGL/C&P//4100004147/14/PM | 01.09.2014 | 30.04.2015 | 3975280 | 2639389 | 8 | 66.395 | COMPLETED
10 | M/S MAHANAGAR GAS LTD., | Laying of MDPE Pipeline for City Gas Distribution Network and Installation of Service Regulator, Regulating Station for domestic & Non Domestic customers in North zone Mumbai Area. | MGL/C&P/CA1 PRJECTS/1098/14-15/PM Dated: 24.12.2014 | MGL/C&P//4100004688/15/PM | 02.05.2015 | 01.10.2015 | 1986991 | 1364226 | 5 | 68.6579 | COMPLETED
11 | M/S MAHANAGAR GAS LTD., | Erection of GI Pipe, Copper Tube, Installation of Gas Meter, Rubber Hose, Valves etc. for supply of Piped Natural Gas inside the kitchen for Domestic customers in North zone C Mumbai Area. | MGL/C&P/CA1 PRJECTS/0928/14-15/PM Dated: 04.08.2014 | MGL/C&P//4100004671/15/PM | 24.04.2015 | 23.09.2015 | 1987752 | 1963250 | 5 | 98.7674 | COMPLETED
12 | M/S MAHANAGAR GAS LTD., | Erection of GI Pipe, Copper Tube, Installation of Gas Meter, Rubber Hose, Valves etc. for supply of Piped Natural Gas inside the kitchen for Domestic customers in North zone C Mumbai Area. | MGL/C&P//4100004870/15/PM | MGL/C&P//4100004870/15/PM | 27.07.2015 | 26.09.2015 | 498050 | 430370 | 2 | 86.411 | COMPLETED
13 | M/S MAHANAGAR GAS LTD., | MP/LP GI Installation of SR,RS,Gas Meter, Copper Tube, Rubber Hose,Valves etc. for Providing PNG for Domestic & Non domestic Customer in Mumbai Area | MGL/C&P/PLNG/1405/15-16/PM Dated: 28.08.2015 | MGL/C&P/410000 5009/2015-16/HJ | 01.10.2015 | 30.09.2016 | 14125943 | 14446972.81 | 12 | 102.2726 | WORK IN PROGRESS
14 | M/S MAHANAGAR GAS LTD., | MP/LP GI Installation of SR,RS,Gas Meter, Copper Tube, Rubber Hose,Valves etc. for Providing PNG for Domestic & Non domestic Customer in Mumbai Area | MGL/C&P/PLNG/1405/15-16/PM Dated: 28.08.2015 | MGL/C&P/410000 5011/2015-16/HJ | 01.10.2015 | 30.09.2016 | 14504898 | 3938147.15 | 12 | 27.1505 | WORK IN PROGRESS
15 | M/S MAHANAGAR GAS LTD., | MP/LP GI Installation of SR,RS,Gas Meter, Copper Tube, Rubber Hose,Valves etc. for Providing PNG for Domestic & Non domestic Customer in Mumbai Area | MGL/C&P/PLNG/1447/15-16/PM Dated: 29.10.2015 | MGL/C&P/410000 5102/2015-16/HJ | 01.11.2015 | 31.10.2016 | 21526350 | 6142229.73 | 12 | 28.5335 | WORK IN PROGRESS
16 | M/S MAHANAGAR GAS LTD., | Providing PNG connections from existing gasified risers (Online Tap-off.) of GI Pipe Network in e D Thane & Mira Road Area | MGL/C&P/PLNG/1404/15-16/PM Dated: 13.10.2015 | MGL/C&P/410000 5043/15-16/PM | 01.10.2015 | 30.09.2016 | 2658500 | 1542147.9 | 12 | 58.0082 | WORK IN PROGRESS
17 | M/S AAVANTIKA GAS LTD., | Work of O&M -PNG MDPE Network for Indore,Ujjain & Gwalior CGDP | 0503/AGL/WO/O&M/PNG/FP/2015 | 0503/AGL/WO/O&M/PNG/FP/2015 | 05.10.2015 | 04.10.2017 | 23359421 | 5989640 | 24 | 25.6412 | WORK IN PROGRESS
18 | M/S AAVANTIKA GAS LTD., | Work Pertaining to Patrolling of Steel / MDPE Pipe line Network of Ujjain & Pithampur CGDP | 0506/AGL/LOI/Patrolling/FP/UJJ/PTM/2015 | 0506/AGL/LOI/Patrolling/FP/UJJ/PTM/2015 | 05.10.2015 | 04.10.2017 | 6073920 | 1776000 | 24 | 29.2398 | WORK IN PROGRESS
For M/s Future Projects
Bhanu Singh
Proprietor
Mob-09322862988